## Sheet1
Project ID | Project External ID | Project Name | Client Name | Project Status | Project Category | Billing method | Sold budget | Sold budget Currency | Days sold | Real to date | Slippage to date | Planned to term | Advancement rate | Margin rate to term | Staffed Days | Daily Fee | Daily Fee Currency | Custom Daily Cost | Staffing Rate | Business Unit
1 | 1206 | Project 1 | Client A | Signed | Projet Client | time_and_materials | 20261 | TND | 147 | 106 | 36 | 163 | 65.43 | 28 | 32 | 963 | TND | 303 | 50.53 | Finance
2 | 3779 | Project 2 | Client C | Signed | Projet Interne | fixed_price | 13069 | TND | 127 | 33 | 14 | 78 | 91.99 | 15.42 | 44 | 397 | TND | 195 | 58.64 | Audit
3 | 3352 | Project 3 | Client B | Signed | Projet Interne | fixed_price | 22773 | TND | 121 | 69 | 8 | 193 | 53.23 | 9.4 | 146 | 749 | TND | 474 | 80.02 | Audit
4 | 3440 | Project 4 | Client C | Signed | Projet Client | fixed_price | 27378 | TND | 50 | 40 | 42 | 102 | 89.98 | 21.08 | 62 | 826 | TND | 333 | 96.29 | Consulting
5 | 1020 | Project 5 | Client B | Signed | Projet Interne | time_and_materials | 11736 | TND | 169 | 10 | 14 | 74 | 65.01 | 19.42 | 69 | 590 | TND | 301 | 64.33 | Audit
6 | 4460 | Project 6 | Client C | Signed | Projet Interne | fixed_price | 35349 | TND | 186 | 45 | 5 | 158 | 61.85 | 9.83 | 37 | 503 | TND | 430 | 93.66 | Audit
7 | 1413 | Project 7 | Client B | Signed | Projet Client | time_and_materials | 42241 | TND | 131 | 107 | 25 | 83 | 97.07 | 20.66 | 91 | 779 | TND | 484 | 60.93 | RH
8 | 3581 | Project 8 | Client C | Open | Projet Client | fixed_price | 11170 | TND | 68 | 105 | 32 | 114 | 59.72 | 13.33 | 42 | 487 | TND | 294 | 61.57 | RH
9 | 4899 | Project 9 | Client A | Open | Projet Interne | fixed_price | 45366 | TND | 54 | 19 | 0 | 94 | 48.45 | 24.97 | 28 | 456 | TND | 251 | 75.25 | RH
10 | 1399 | Project 10 | Client B | Signed | Projet Client | fixed_price | 16848 | TND | 116 | 114 | 37 | 150 | 99.05 | 13.74 | 147 | 527 | TND | 481 | 63.2 | RH
11 | 2452 | Project 11 | Client C | Open | Projet Interne | time_and_materials | 25801 | TND | 152 | 107 | 18 | 55 | 75.17 | 13.57 | 149 | 874 | TND | 809 | 52.27 | RH
12 | 4764 | Project 12 | Client C | Signed | Projet Interne | fixed_price | 27469 | TND | 128 | 30 | 8 | 90 | 80.42 | 12.49 | 91 | 159 | TND | 869 | 75.53 | RH
13 | 4458 | Project 13 | Client A | Open | Projet Interne | fixed_price | 29228 | TND | 71 | 76 | 7 | 127 | 22.96 | 23.49 | 39 | 402 | TND | 74 | 97.2 | RH
14 | 2633 | Project 14 | Client B | Signed | Projet Interne | time_and_materials | 32663 | TND | 195 | 58 | 21 | 84 | 67.32 | 7.58 | 123 | 275 | TND | 551 | 58.09 | RH
15 | 4726 | Project 15 | Client A | Open | Projet Client | time_and_materials | 48483 | TND | 151 | 45 | 29 | 105 | 44.01 | 15.33 | 38 | 645 | TND | 897 | 54.84 | RH
16 | 3804 | Project 16 | Client C | Open | Projet Interne | fixed_price | 24851 | TND | 136 | 124 | 18 | 162 | 82.37 | 6.83 | 90 | 518 | TND | 208 | 91.61 | RH
17 | 1148 | Project 17 | Client C | Open | Projet Interne | time_and_materials | 44500 | TND | 114 | 123 | 47 | 81 | 45.57 | 20.91 | 128 | 834 | TND | 497 | 63.18 | RH
18 | 4419 | Project 18 | Client A | Open | Projet Interne | fixed_price | 48847 | TND | 66 | 55 | 0 | 142 | 46.13 | 14.97 | 30 | 261 | TND | 717 | 55.54 | RH
19 | 2256 | Project 19 | Client B | Signed | Projet Interne | time_and_materials | 26681 | TND | 160 | 130 | 22 | 67 | 44.62 | 25.97 | 131 | 535 | TND | 705 | 70.13 | RH
20 | 2969 | Project 20 | Client C | Signed | Projet Client | time_and_materials | 16421 | TND | 59 | 113 | 26 | 165 | 12.08 | 10.6 | 45 | 612 | TND | 793 | 90.69 | RH
21 | 3814 | Project 21 | Client B | Signed | Projet Client | fixed_price | 31776 | TND | 176 | 86 | 1 | 110 | 62.47 | 17.64 | 115 | 709 | TND | 653 | 77.02 | RH
22 | 3814 | Project 22 | Client B | Open | Projet Interne | time_and_materials | 32870 | TND | 64 | 127 | 36 | 178 | 35.93 | 16.2 | 68 | 151 | TND | 825 | 53.31 | RH
23 | 1115 | Project 23 | Client B | Signed | Projet Interne | time_and_materials | 13998 | TND | 186 | 39 | 47 | 89 | 25.56 | 16.05 | 149 | 566 | TND | 870 | 88.43 | RH
24 | 2457 | Project 24 | Client B | Open | Projet Client | fixed_price | 19777 | TND | 158 | 64 | 17 | 138 | 13.79 | 25.84 | 80 | 745 | TND | 378 | 93.22 | Audit
25 | 3272 | Project 25 | Client C | Open | Projet Client | fixed_price | 20450 | TND | 178 | 55 | 1 | 189 | 32.89 | 8.13 | 62 | 790 | TND | 453 | 62.09 | Consulting
26 | 4319 | Project 26 | Client C | Open | Projet Interne | time_and_materials | 15591 | TND | 161 | 26 | 1 | 117 | 98.17 | 6.57 | 92 | 207 | TND | 614 | 66.56 | IT
27 | 1435 | Project 27 | Client A | Signed | Projet Client | fixed_price | 34587 | TND | 55 | 94 | 20 | 50 | 70.98 | 6.66 | 98 | 299 | TND | 89 | 73.32 | HR
28 | 1579 | Project 28 | Client C | Signed | Projet Client | time_and_materials | 46891 | TND | 72 | 20 | 45 | 182 | 42.02 | 15.71 | 102 | 513 | TND | 316 | 54.56 | Consulting
29 | 1459 | Project 29 | Client B | Signed | Projet Client | fixed_price | 32575 | TND | 58 | 31 | 27 | 145 | 55.29 | 17.2 | 98 | 810 | TND | 682 | 73.67 | Finance
30 | 1579 | Project 30 | Client B | Open | Projet Client | time_and_materials | 38658 | TND | 143 | 92 | 34 | 73 | 76.3 | 17.85 | 28 | 852 | TND | 742 | 99.37 | HR
31 | 1011 | Project 31 | Client C | Signed | Projet Interne | time_and_materials | 27684 | TND | 51 | 119 | 39 | 182 | 79.59 | 25.31 | 23 | 731 | TND | 280 | 98.52 | Consulting
32 | 3149 | Project 32 | Client B | Open | Projet Interne | fixed_price | 37367 | TND | 158 | 18 | 47 | 78 | 10.65 | 8 | 45 | 625 | TND | 627 | 54.69 | IT
33 | 3950 | Project 33 | Client A | Open | Projet Interne | time_and_materials | 28822 | TND | 141 | 148 | 20 | 74 | 86.49 | 23.47 | 74 | 841 | TND | 654 | 97.27 | Consulting
34 | 4426 | Project 34 | Client C | Open | Projet Interne | fixed_price | 23537 | TND | 59 | 88 | 46 | 89 | 14.37 | 9.97 | 22 | 245 | TND | 401 | 53.66 | HR
35 | 3811 | Project 35 | Client B | Signed | Projet Interne | time_and_materials | 39436 | TND | 118 | 147 | 15 | 165 | 66.4 | 28.49 | 62 | 714 | TND | 805 | 52.63 | Audit
36 | 2893 | Project 36 | Client B | Open | Projet Interne | fixed_price | 36891 | TND | 191 | 13 | 3 | 91 | 22.39 | 27.69 | 101 | 632 | TND | 615 | 65.1 | Consulting
37 | 4520 | Project 37 | Client B | Open | Projet Client | fixed_price | 48549 | TND | 166 | 90 | 8 | 102 | 32.38 | 11.28 | 137 | 236 | TND | 315 | 99.49 | Consulting
38 | 1760 | Project 38 | Client B | Open | Projet Client | time_and_materials | 43255 | TND | 161 | 105 | 3 | 66 | 27.81 | 10.63 | 30 | 708 | TND | 394 | 55.41 | Finance
39 | 2893 | Project 39 | Client A | Open | Projet Interne | time_and_materials | 41824 | TND | 79 | 51 | 7 | 115 | 69.2 | 22.6 | 49 | 714 | TND | 807 | 69.59 | Finance
40 | 3074 | Project 40 | Client C | Open | Projet Interne | fixed_price | 25951 | TND | 129 | 82 | 10 | 175 | 97.85 | 20.37 | 32 | 828 | TND | 244 | 76.37 | HR
41 | 2319 | Project 41 | Client A | Signed | Projet Interne | fixed_price | 46081 | TND | 178 | 47 | 35 | 140 | 22.45 | 8.36 | 52 | 549 | TND | 217 | 86.55 | Audit
42 | 4535 | Project 42 | Client A | Signed | Projet Client | fixed_price | 42719 | TND | 97 | 85 | 33 | 174 | 19.19 | 16.56 | 32 | 629 | TND | 604 | 89.55 | Finance
43 | 2763 | Project 43 | Client B | Signed | Projet Interne | time_and_materials | 47418 | TND | 68 | 16 | 18 | 74 | 90.05 | 10 | 27 | 156 | TND | 388 | 88.36 | IT
44 | 4520 | Project 44 | Client A | Signed | Projet Client | fixed_price | 41511 | TND | 68 | 42 | 5 | 136 | 64.34 | 24.4 | 73 | 474 | TND | 335 | 86.63 | HR
45 | 2529 | Project 45 | Client A | Open | Projet Client | time_and_materials | 46224 | TND | 89 | 104 | 25 | 56 | 27.25 | 8.08 | 119 | 119 | TND | 248 | 56.85 | IT
46 | 1721 | Project 46 | Client B | Signed | Projet Client | fixed_price | 45208 | TND | 143 | 59 | 18 | 160 | 21.73 | 8.95 | 96 | 433 | TND | 464 | 80.25 | IT
47 | 1438 | Project 47 | Client C | Signed | Projet Client | time_and_materials | 17064 | TND | 141 | 148 | 22 | 139 | 34.98 | 22.8 | 68 | 690 | TND | 269 | 50.97 | IT
48 | 3230 | Project 48 | Client A | Signed | Projet Client | time_and_materials | 44837 | TND | 104 | 47 | 8 | 132 | 80.98 | 29.53 | 144 | 487 | TND | 896 | 77.41 | Audit
49 | 1946 | Project 49 | Client A | Open | Projet Interne | fixed_price | 14413 | TND | 147 | 144 | 19 | 158 | 72.52 | 15.51 | 127 | 231 | TND | 179 | 86.03 | IT
50 | 2502 | Project 50 | Client A | Signed | Projet Interne | time_and_materials | 34756 | TND | 182 | 85 | 2 | 193 | 14 | 28.11 | 22 | 591 | TND | 555 | 51.43 | HR
51 | 2657 | Project 51 | Client A | Signed | Projet Interne | time_and_materials | 31905 | TND | 73 | 87 | 2 | 145 | 70.66 | 28.11 | 38 | 786 | TND | 272 | 96.34 | IT
52 | 4393 | Project 52 | Client C | Signed | Projet Client | time_and_materials | 22520 | TND | 126 | 149 | 19 | 173 | 43.09 | 27.25 | 123 | 465 | TND | 444 | 62.07 | IT
53 | 3265 | Project 53 | Client B | Open | Projet Client | time_and_materials | 24129 | TND | 179 | 34 | 26 | 86 | 90.34 | 27.41 | 84 | 742 | TND | 371 | 57.4 | Consulting
54 | 4324 | Project 54 | Client A | Signed | Projet Interne | fixed_price | 31095 | TND | 77 | 124 | 12 | 170 | 81.85 | 14.17 | 66 | 282 | TND | 464 | 85.41 | Audit
55 | 2856 | Project 55 | Client A | Signed | Projet Client | fixed_price | 19399 | TND | 151 | 46 | 40 | 175 | 52.38 | 17.92 | 68 | 376 | TND | 696 | 81.19 | HR
56 | 1739 | Project 56 | Client B | Open | Projet Interne | fixed_price | 18037 | TND | 151 | 35 | 24 | 151 | 46.24 | 27.89 | 39 | 553 | TND | 714 | 90.4 | Consulting
57 | 4214 | Project 57 | Client C | Open | Projet Client | time_and_materials | 40009 | TND | 186 | 135 | 31 | 148 | 34.2 | 24.24 | 91 | 635 | TND | 283 | 85.78 | Audit
58 | 2525 | Project 58 | Client C | Open | Projet Client | time_and_materials | 25921 | TND | 137 | 44 | 12 | 81 | 88.62 | 29.55 | 34 | 621 | TND | 370 | 75.55 | Finance
59 | 4294 | Project 59 | Client A | Open | Projet Client | time_and_materials | 32250 | TND | 170 | 31 | 17 | 138 | 22.5 | 26.79 | 86 | 721 | TND | 456 | 62.11 | Audit
60 | 4488 | Project 60 | Client B | Signed | Projet Interne | fixed_price | 28743 | TND | 128 | 39 | 30 | 139 | 77.43 | 22.39 | 102 | 315 | TND | 144 | 92.69 | HR
61 | 3103 | Project 61 | Client C | Open | Projet Client | fixed_price | 36887 | TND | 143 | 93 | 16 | 148 | 53.93 | 18.19 | 101 | 372 | TND | 690 | 80.11 | Consulting
62 | 2907 | Project 62 | Client C | Open | Projet Interne | fixed_price | 30854 | TND | 85 | 53 | 28 | 196 | 42.84 | 8.87 | 60 | 868 | TND | 455 | 90.59 | HR
63 | 4332 | Project 63 | Client C | Signed | Projet Client | time_and_materials | 49274 | TND | 187 | 78 | 8 | 196 | 69.33 | 15.73 | 110 | 851 | TND | 507 | 92.17 | Audit
64 | 4621 | Project 64 | Client A | Open | Projet Client | fixed_price | 33881 | TND | 66 | 25 | 0 | 65 | 11.42 | 19.38 | 60 | 530 | TND | 485 | 99.14 | IT
65 | 3304 | Project 65 | Client A | Open | Projet Client | time_and_materials | 44043 | TND | 151 | 92 | 32 | 86 | 31.14 | 21.89 | 57 | 170 | TND | 663 | 77.36 | Finance
66 | 2053 | Project 66 | Client B | Open | Projet Client | time_and_materials | 32096 | TND | 72 | 122 | 16 | 191 | 80.98 | 6.02 | 91 | 148 | TND | 278 | 86.9 | Consulting
67 | 2036 | Project 67 | Client A | Open | Projet Client | fixed_price | 41801 | TND | 73 | 91 | 33 | 144 | 56.62 | 19.31 | 117 | 148 | TND | 816 | 94.65 | Consulting
68 | 4338 | Project 68 | Client B | Signed | Projet Interne | time_and_materials | 47930 | TND | 159 | 72 | 25 | 135 | 44.49 | 16 | 58 | 609 | TND | 53 | 90.26 | Finance
69 | 3472 | Project 69 | Client B | Signed | Projet Client | time_and_materials | 45152 | TND | 173 | 117 | 0 | 101 | 86.82 | 14.99 | 48 | 885 | TND | 761 | 95.38 | Consulting
70 | 4765 | Project 70 | Client B | Open | Projet Client | time_and_materials | 18186 | TND | 78 | 33 | 44 | 154 | 38.42 | 21.22 | 27 | 938 | TND | 548 | 75.79 | Finance