## Sheet1
Project ID | Project External ID | Project Name | Client Name | Project Status | Project Category | Project Description | Project Trello Column | Estimated start | Estimated end | Project Trello Labels | Project Creator | Project Co-Owner | Billing method | Sold budget | Sold budget Currency | Business Unit (Project) | Days sold | Real to date | Slippage to date | Slippage projected | Planned to term | Advancement rate | Margin rate to term | Secteur d'activité | Engagement Manager | Engagement Partner | Fiscal Year | Recurring Project | Temporary | Rollforward | Validated Project | Validation Manager | Validation Partner | Code client | Date d’expiration SAN | SAN | Date d’approbation CEAC mission | Taxonomie | Code SAN
45 |  | Test 2 | zitouna |  | Externe |  | Waiting List | 10-06-2024 | 28-06-2024 | N/A | Samar BEN REJAB | N/A | Régie | 3000 | TND | Audit MH | 10 | 16.71 | -8.29 | 6.71 | 25 | 0.29 | -5.85 | Banques | [9 empty] | XXXXXXXXXXXXX | XXXXXXXXXXXXXXX | XXXXXXXXXXXXXX | XXXXXXXXXXXXXXX | XXXXXXXXXXXXXXXXX | XXXXXXXXXXXXXXXXXX
46 |  | Test 1 | Amen BANQUE |  | Externe | MIssion de CAC de la société "XXXXX" pour l'année 2025 | interne | 20-05-2024 | 24-05-2024 | N/A | Asma Khairallah | Sandra 2 REKIK | Régie | 5000 | TND | Audit, TMC IT Audit | 2 | 12.13 | 10.13 | 10.13 | 2 | 0 | 0 | [10 empty] | XXXXXXXXXXX | XXXXXXXXXXXX | XXXXXXXXXXXX | XXXXXXXXXXXXXX | XXXXXXXXXXXXX | XXXXXXXXXXXX
47 |  | D365 - Amen | Amen BANQUE |  |  |  | Waiting List | 01-01-2024 | 04-10-2024 | N/A |  | N/A | Autre |  |  | N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | [10 empty] | 1234 | 10/06/2024 | 1234 | 10/06/2024 | 1234 | 1234
49 |  | RIM | AMI ASSUANCE |  | Externe |  | Waiting List | 01-05-2024 | 31-05-2024 | N/A | Rim BEN HAMIDA | Rim BEN HAMIDA | Régie | 10000 | TND | Audit | 35 | 29.5 | 14.5 | -5.5 | 15 | 2.95 | 0.83 | Assurances | [9 empty] | XX | XX | XX | XX | XX | XX
50 |  | RH ACADEMY | BANQUE RH |  | Externe |  | Waiting List | 01-04-2024 | 28-06-2024 | N/A | Wiem BELKHOUJA | Wiem BELKHOUJA | Forfait | 1500000 | TND | Audit | 110 | 122.5 | -24.5 | 12.5 | 147 | 1 | -5.75 | Banques | [9 empty] | XXXXXXXXXXXXXXXXXXXXXX | XXXXXXXXXXXXXXXX | XXXXXXXXXXXXXXXXXXXXXXXXXX | XXXXXXXXXXXXXXXXXXXXX | XXXXXXXXXXXXXXXXXXXX | XXXXXXXXXXXXXXXXXX
51 |  | Asma 2 | Amen BANQUE |  |  |  | Waiting List | 10-06-2024 | 28-06-2024 | N/A | Asma Khairallah | Rim BEN HAMIDA | Régie | 20000 | TND | N/A | 0 | 0 | -4 |  | 4 | 0 | 0 | [10 empty] | xxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxx | xxxxxxxxxxxxxxxxxxx | xxxxxxxxxxxx | xxxxxxxxxxxx
52 |  | TEST PILOTAGE | PILOTAGE |  | Externe |  | Waiting List | 01-05-2024 | 31-05-2024 | N/A | Wiem BELKHOUJA | Wiem BELKHOUJA | Forfait | 150000 | TND | Deal Advisory | 15 | 0 | -23 | -15 | 23 | 0 | 0 | Education | [9 empty] | XXXXXXXXXXXXXXX | XXXXXXXXXXXXXXXX | XXXXXXXXXXXXXXXXXX | XXXXXXXXXXXXXXXXXXXXXXXXXXXX | XXXXXXXXXXXXXXXXXXXXXXXXX | XXXXXXXXXXXXXXXXXX
53 |  | CAC - KPMG 2025 | KPMG Tunisie |  | Projet Client | Comisariat au comptes de KPMG pour 2025 | Waiting List | 27-05-2024 | 31-05-2024 | N/A | Sandra 2 REKIK | Sandra 2 REKIK | Régie | 5000 | TND | Audit | 2 | 0 | 0 | -2 | 0 | 0 | 0 | [10 empty] | XXXX | XXXX | XXXXXX | XXX | XX | XXXXXX
54 |  | CAC 2025 | Amen BANQUE |  |  |  | Waiting List | 20-05-2024 | 28-05-2024 | N/A | Asma Khairallah | N/A | Forfait | 50000 | TND | Audit | 0 | 10 | -5 |  | 15 | 1 | 0.87 | [10 empty] | xxxxxxxxxxxxx | xxxxxxxxxxxx | xxxxxxxxxxx | xxxxxxxxxxxx | xxxxxxxxxx | xxxxxxxxxx
55 |  | Intérim 2025 | Amen BANQUE |  | Projet Client |  | Waiting List | 21-05-2024 | 23-05-2024 | N/A | Asma Khairallah | Wiem BELKHOUJA EP KHEMIRI, Mohamed HZAMI | Forfait | 20000 | TND | Audit | 0 | 6.63 | -20.38 |  | 27 | 1 | 0.78 |  | Wiem BELKHOUJA EP KHEMIRI - wbelkhouja@kpmg.com | Mohamed HZAMI - mhzami@kpmg.com |  |  |  |  | Validated | SUBMITTED | VALIDATED | xxxxxxxx | xxxxxxxxxxx | xxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxx | xxxxxxxxx
56 |  | Final 2025 | Amen BANQUE |  |  |  | Waiting List | 24-05-2024 | 28-05-2024 | N/A | Asma Khairallah | N/A | Forfait | 30000 | TND | N/A | 0 | 5 | -9 |  | 14 | 1 | 0.83 | [10 empty] | xxxxxxxxxxxxxx | xxxxxxxxxx | xxxxxxxxxxx | xxxxxxxxxxxxxx | xxxxxxxxxxxx | xxxxxxxxxxxxx
57 |  | CAC 2025 | ZIT |  | Projet Client |  | interne | 27-05-2024 | 02-08-2024 | N/A | Samar BEN REJAB | Wiem BELKHOUJA | Régie | 100000 | TND | Audit | 20 | 0 | -158.5 | -20 | 158.5 | 0 | 0 | Banques | [9 empty] | XXXXXXXXXXXXX | XXXXXXXXXX | VVVVVVVVVV | VVVVVVVVVV | VVVVVVVVVVVVVV | CCCCCC
58 |  | CAC BCT | BANQUE CENTRALE |  | Projet Client |  | Waiting List | 13-06-2024 | 12-07-2024 | N/A | Rim BEN HAMIDA | Samar BEN REJAB, Wiem BELKHOUJA, Anis CHABIR | Régie | 10000 | TND | Audit | 45 | 18.25 | -91.75 | -26.75 | 110 | 1.83 | 0.56 | Banques | [9 empty] | xxxxxxxx | xxxxxxxxxxx | xxxxxxxxxxxx | xxxxxxxxxxx | xxxxxxxxx | xxxxxxxxxx
59 |  | Projet Test | Client02 |  |  |  | Waiting List | 29-05-2024 | 13-06-2024 | N/A | Rim BEN HAMIDA | N/A | Autre |  |  | N/A | 0 | 0 | -22 |  | 22 | 0 | 0 | [10 empty] | d | d | d | d | d | d
60 |  | SMEA | KPMG Tunisie |  |  |  | Waiting List | 28-06-2024 | 02-08-2024 | N/A | Mohamed Amine SOUID | Mohamed Amine SOUID | Autre | 50000 | TND | Audit SM | 0 | 0 | -18 |  | 18 | 0 | 0 | Industrie Automobile | Mohamed Amine SOUID - asouid@kpmg.com | [8 empty] | SMEA | cccc | xxxxx | cccc | ccc | xxx
61 |  | TAX | TEST |  | Projet Client |  | Waiting List | 28-06-2024 | 26-07-2024 | N/A | Slim BESBES | Noureddine BOUABID | Forfait | 10000 | TND | Tax | 40 | 0 | -31 | -40 | 31 | 0 | 0 | Industrie Automobile | [9 empty] | XXXXX | XXXXXXX | XXXXX | XXXXXXXX | XXXXXXX | XXXXX
62 |  | Administratif | KPMG Tunisie |  | Interne |  | interne | 27-06-2024 | 31-12-2024 | N/A | Slim BESBES | Slim BESBES | Autre |  |  | N/A | 0 | 0.25 | -13.05 |  | 13.3 | 0 | 0 | [10 empty] | X | X | XX | X | X | XX
67 |  | Test3 | Napta |  | Activité interne Adm - Finance |  | Waiting List | 03-07-2024 | 19-07-2024 | N/A | Rim BEN HAMIDA | N/A | Autre |  |  | ADM | 0 | 5 | -32 |  | 37 | 0 | 0 | [10 empty] | s | s | S | s | s | q
68 |  | CFAO Roll Out | KPMG Tunisie |  | Projet Client | dd | Waiting List | 19-06-2024 | 06-09-2030 | N/A | Malek HARBAOUI | Samar BEN REJAB, Malek HARBAOUI | Régie | 10000000 | TND | TMC TECH | 1100 | 0 | 0 | -1100 | 0 | 0 | 0 | Industrie Automobile | Malek HARBAOUI - mharbaoui@kpmg.com | [8 empty] | 1226 | dd | dd | dd | dd | dd